## Dashboard
PROJECT EXECUTION TRACKER — DASHBOARD
As of 13 March 2026 ¦ 63 total tasks across 8 workstreams
63 | 8 | 10 | 14 | 26 | 1
TOTAL TASKS | OVERDUE | DUE TODAY | UPCOMING (3d) | SCHEDULED | DONE
TASKS BY WORKSTREAM
Workstream | Total | Overdue | On Track | Visual Load
Conv % | 8 | 3 | 5 | ████████
Current Team Phsycological Alignment | 8 | 0 | 8 | ████████
End to end tech chain | 4 | 0 | 4 | ████
Expand Right Sales Team | 9 | 0 | 9 | █████████
Geo Politics | 13 | 4 | 9 | █████████████
No Operation Head | 8 | 0 | 8 | ████████
Refund Process | 3 | 0 | 3 | ███
Unified Data System, Reporting & Analysis | 10 | 1 | 9 | ██████████
OWNER WORKLOAD
Owner | Total | Overdue | Load Bar
Anushka | 13 | 0 | █████████████
Archit | 4 | 0 | ████
Bhavna | 6 | 0 | ██████
Bhavna/Tarun | 1 | 0 | █
Deeksha | 4 | 1 | ████ ⚠
Deeksha/Tarun | 1 | 1 | █ ⚠
Loyana | 5 | 0 | █████
Nandkishore | 10 | 4 | ██████████ ⚠
Sachin | 4 | 0 | ████
Tarun | 14 | 2 | ██████████████ ⚠
NEXT 7 DAYS — CRITICAL DEADLINES
Date | Task | Owner | Workstream | Status
2026-03-13 | Creating Operation Process for FIT | Bhavna | Geo Politics | Due Today
2026-03-13 | FIT Operation Executive Alignment | Tarun | Geo Politics | Due Today
2026-03-13 | USP, Etc) | Bhavna | Geo Politics | Due Today
2026-03-13 | Cancellation / Date Change / Credit Note Issuance / Etc. | Bhavna/Tarun | Geo Politics | Due Today
2026-03-13 | Process Handover to Ops Person By Product (OPS KRA) | Bhavna | Geo Politics | Due Today
2026-03-13 | B2B Air Deals (to Check) | - | Geo Politics | Due Today
2026-03-13 | Survey of Seller | Loyana | Conv % | Due Today
2026-03-13 | GIT Booking Portal | Sachin | End to end tech chain | Due Today
2026-03-13 | Including sellers and Ops People | Anushka | Current Team Phsycological Alignment | Due Today
2026-03-13 | Identify the top performers | Anushka | Current Team Phsycological Alignment | Due Today
2026-03-14 | Sales Head Dashboard Requirement to Nandkishore | Tarun | Unified Data System, Reporting & Analysis | Upcoming
2026-03-14 | Marketing Head Dashboard Requirement to Nandkishore | Deeksha | Unified Data System, Reporting & Analysis | Upcoming
2026-03-14 | Product Head Dashboard Requirement to Nandkishore | Bhavna | Unified Data System, Reporting & Analysis | Upcoming
2026-03-14 | Required JD for Operation Head | Tarun | No Operation Head | Upcoming
2026-03-14 | Salary Budget Approval from Karan | Anushka | No Operation Head | Upcoming
2026-03-16 | EOS | Nandkishore | Unified Data System, Reporting & Analysis | Upcoming
2026-03-16 | CEO Dashboard | Nandkishore | Unified Data System, Reporting & Analysis | Upcoming
2026-03-16 | Sales Head Dashboard | Nandkishore | Unified Data System, Reporting & Analysis | Upcoming
2026-03-16 | Marketing Head Dashboard | Nandkishore | Unified Data System, Reporting & Analysis | Upcoming
2026-03-16 | Product Head Dashboard | Nandkishore | Unified Data System, Reporting & Analysis | Upcoming
2026-03-16 | Referral Support / Job posting / Vendor | Anushka | No Operation Head | Upcoming
2026-03-16 | Creating SOP of Hiring | Anushka | No Operation Head | Upcoming
2026-03-16 | Take Approval from Karan for people to put on PIP | Loyana | Current Team Phsycological Alignment | Upcoming
2026-03-16 | Take reward approval from Karan | Loyana | Current Team Phsycological Alignment | Upcoming
2026-03-17 | Approving SOP of hiring | Tarun | No Operation Head | Scheduled
2026-03-17 | (Clear Old Dues) | Tarun | Current Team Phsycological Alignment | Scheduled
2026-03-17 | Shortlisting of 10 agencies | Tarun | Expand Right Sales Team | Scheduled
2026-03-17 | Identify issues | Loyana | Current Team Phsycological Alignment | Scheduled
2026-03-18 |  | Archit | Geo Politics | Scheduled
2026-03-18 | Selection of FIT & GIT Sellers (Pilot Pod) | Tarun | Conv % | Scheduled
2026-03-18 | SOP/ Process of Issuing Refunds | Archit | Refund Process | Scheduled
2026-03-18 | Physical meet with the PIP Sellers | Anushka | Current Team Phsycological Alignment | Scheduled
2026-03-18 | Cashflow Visibility | Sachin | End to end tech chain | Scheduled
2026-03-18 | Phase 1 (CRM Automations live) | Deeksha | Conv % | Scheduled
2026-03-19 | Take the inhouse pod hiring requirements from Tarun | Anushka | Expand Right Sales Team | Scheduled
2026-03-20 | Supply | Bhavna | Geo Politics | Scheduled
2026-03-20 | From suppliers as a credit note to cx | Bhavna | Geo Politics | Scheduled
2026-03-20 | Get rewards delivered | Loyana | Current Team Phsycological Alignment | Scheduled

## Master Task List
# | Issue / Workstream | Task | Owner | Deadline | Status | Week # | Days Left
1 | Geo Politics | Ladakh / Sikkim | Tarun | 2026-03-11 | Overdue | 11 | -2
2 | Geo Politics | Shortlisting of Destinations : Domestic / International | Tarun | 2026-03-11 | Overdue | 11 | -2
3 | Conv % | Pre Sales TELECRM SETUP DEMO (L1) | Nandkishore | 2026-03-11 | Overdue | 11 | -2
4 | Conv % | Lead Allocation Fix in TELECRM (L1) | Nandkishore | 2026-03-11 | Overdue | 11 | -2
5 | Unified Data System, Reporting & Analysis | L10 Scorecard | Nandkishore | 2026-03-12 | Overdue | 11 | -1
6 | Geo Politics | Budget distribution current and domestic | Deeksha/Tarun | 2026-03-12 | Overdue | 11 | -1
7 | Geo Politics | Revised Lead change live in the campaigns | Deeksha | 2026-03-12 | Overdue | 11 | -1
8 | Conv % | Sales SLA tracker Live | Nandkishore | 2026-03-12 | Overdue | 11 | -1
9 | Geo Politics | Creating Operation Process for FIT | Bhavna | 2026-03-13 | Due Today | 11 | 0
10 | Geo Politics | FIT Operation Executive Alignment | Tarun | 2026-03-13 | Due Today | 11 | 0
11 | Geo Politics | USP, Etc) | Bhavna | 2026-03-13 | Due Today | 11 | 0
12 | Geo Politics | Cancellation / Date Change / Credit Note Issuance / Etc. | Bhavna/Tarun | 2026-03-13 | Due Today | 11 | 0
13 | Geo Politics | Process Handover to Ops Person By Product (OPS KRA) | Bhavna | 2026-03-13 | Due Today | 11 | 0
14 | Geo Politics | B2B Air Deals (to Check) | - | 2026-03-13 | Due Today | 11 | 0
15 | Conv % | Survey of Seller | Loyana | 2026-03-13 | Due Today | 11 | 0
16 | End to end tech chain | GIT Booking Portal | Sachin | 2026-03-13 | Due Today | 11 | 0
17 | Current Team Phsycological Alignment | Including sellers and Ops People | Anushka | 2026-03-13 | Due Today | 11 | 0
18 | Current Team Phsycological Alignment | Identify the top performers | Anushka | 2026-03-13 | Due Today | 11 | 0
19 | Unified Data System, Reporting & Analysis | Sales Head Dashboard Requirement to Nandkishore | Tarun | 2026-03-14 | Upcoming | 11 | 1
20 | Unified Data System, Reporting & Analysis | Marketing Head Dashboard Requirement to Nandkishore | Deeksha | 2026-03-14 | Upcoming | 11 | 1
21 | Unified Data System, Reporting & Analysis | Product Head Dashboard Requirement to Nandkishore | Bhavna | 2026-03-14 | Upcoming | 11 | 1
22 | No Operation Head | Required JD for Operation Head | Tarun | 2026-03-14 | Upcoming | 11 | 1
23 | No Operation Head | Salary Budget Approval from Karan | Anushka | 2026-03-14 | Upcoming | 11 | 1
24 | Unified Data System, Reporting & Analysis | EOS | Nandkishore | 2026-03-16 | Upcoming | 12 | 3
25 | Unified Data System, Reporting & Analysis | CEO Dashboard | Nandkishore | 2026-03-16 | Upcoming | 12 | 3
26 | Unified Data System, Reporting & Analysis | Sales Head Dashboard | Nandkishore | 2026-03-16 | Upcoming | 12 | 3
27 | Unified Data System, Reporting & Analysis | Marketing Head Dashboard | Nandkishore | 2026-03-16 | Upcoming | 12 | 3
28 | Unified Data System, Reporting & Analysis | Product Head Dashboard | Nandkishore | 2026-03-16 | Upcoming | 12 | 3
29 | No Operation Head | Referral Support / Job posting / Vendor | Anushka | 2026-03-16 | Upcoming | 12 | 3
30 | No Operation Head | Creating SOP of Hiring | Anushka | 2026-03-16 | Upcoming | 12 | 3
31 | Current Team Phsycological Alignment | Take Approval from Karan for people to put on PIP | Loyana | 2026-03-16 | Upcoming | 12 | 3
32 | Current Team Phsycological Alignment | Take reward approval from Karan | Loyana | 2026-03-16 | Upcoming | 12 | 3
33 | No Operation Head | Approving SOP of hiring | Tarun | 2026-03-17 | Scheduled | 12 | 4
34 | Current Team Phsycological Alignment | (Clear Old Dues) | Tarun | 2026-03-17 | Scheduled | 12 | 4
35 | Expand Right Sales Team | Shortlisting of 10 agencies | Tarun | 2026-03-17 | Scheduled | 12 | 4
36 | Current Team Phsycological Alignment | Identify issues | Loyana | 2026-03-17 | Scheduled | 12 | 4
37 | Geo Politics |  | Archit | 2026-03-18 | Scheduled | 12 | 5
38 | Conv % | Selection of FIT & GIT Sellers (Pilot Pod) | Tarun | 2026-03-18 | Scheduled | 12 | 5
39 | Refund Process | SOP/ Process of Issuing Refunds | Archit | 2026-03-18 | Scheduled | 12 | 5
40 | Current Team Phsycological Alignment | Physical meet with the PIP Sellers | Anushka | 2026-03-18 | Scheduled | 12 | 5
41 | End to end tech chain | Cashflow Visibility | Sachin | 2026-03-18 | Scheduled | 12 | 5
42 | Conv % | Phase 1 (CRM Automations live) | Deeksha | 2026-03-18 | Scheduled | 12 | 5
43 | Expand Right Sales Team | Take the inhouse pod hiring requirements from Tarun | Anushka | 2026-03-19 | Scheduled | 12 | 6
44 | Geo Politics | Supply | Bhavna | 2026-03-20 | Scheduled | 12 | 7
45 | Geo Politics | From suppliers as a credit note to cx | Bhavna | 2026-03-20 | Scheduled | 12 | 7
46 | Current Team Phsycological Alignment | Get rewards delivered | Loyana | 2026-03-20 | Scheduled | 12 | 7
47 | Conv % | Old Lead Allocation | Tarun | 2026-03-23 | Scheduled | 13 | 10
48 | Expand Right Sales Team | Interviews align & decide panel | Anushka | 2026-03-23 | Scheduled | 13 | 10
49 | Unified Data System, Reporting & Analysis | Realtime Data Integration | Nandkishore | 2026-03-25 | Scheduled | 13 | 12
50 | End to end tech chain | D2C website | Sachin | 2026-03-30 | Scheduled | 14 | 17
51 | Expand Right Sales Team | Meeting 10 agencies | Tarun | 2026-03-31 | Scheduled | 14 | 18
52 | Expand Right Sales Team | Quote Comparisons | Tarun | 2026-03-31 | Scheduled | 14 | 18
53 | Refund Process | Clearing pending payments of partners and vendors | Archit | 2026-03-31 | Scheduled | 14 | 18
54 | Refund Process | Clearing customer refunds | Archit | 2026-03-31 | Scheduled | 14 | 18
55 | Expand Right Sales Team | Allocating the work | Tarun | 1 April | TBD |  | —
56 | No Operation Head | Closing profile and sharing offer letter | Anushka | 1 April | TBD |  | —
57 | Expand Right Sales Team | Role Offers | Anushka | 6 April | TBD |  | —
58 | Expand Right Sales Team | Complete the hiring project | Anushka | 13 April | TBD |  | —
59 | End to end tech chain | FIT Booking Engine | Sachin | 2026-04-15 | Scheduled | 16 | 33
60 | No Operation Head | Planning time wise his/her first 7 days | Anushka | 2026-05-01 | Scheduled | 18 | 49
61 | No Operation Head | DOJ of Candidate | Anushka | 2026-05-01 | Scheduled | 18 | 49
62 | Expand Right Sales Team | Team Live | Tarun | 2026-06-15 | Scheduled | 25 | 94
63 | Conv % | Feedback + Awareness Ads on Live Lead (Trust Based) | Deeksha | Done | Done |  | —

## Owner Dashboard
Owner | Total Tasks | Overdue | Due Today | Upcoming (3d) | Scheduled | Done | % On Track
Anushka | 13 | 0 | 2 | 3 | 5 | 0 | 76.92%
Archit | 4 | 0 | 0 | 0 | 4 | 0 | 100%
Bhavna | 6 | 0 | 3 | 1 | 2 | 0 | 100%
Bhavna/Tarun | 1 | 0 | 1 | 0 | 0 | 0 | 100%
Deeksha | 4 | 1 | 0 | 1 | 1 | 1 | 75%
Deeksha/Tarun | 1 | 1 | 0 | 0 | 0 | 0 | 0%
Loyana | 5 | 0 | 1 | 2 | 2 | 0 | 100%
Nandkishore | 10 | 4 | 0 | 5 | 1 | 0 | 60%
Sachin | 4 | 0 | 1 | 0 | 3 | 0 | 100%
Tarun | 14 | 2 | 1 | 2 | 8 | 0 | 78.57%
OWNER-WISE TASK BREAKDOWN
Anushka
Issue | Task | Deadline | Status
Current Team Phsycological Alignment | Including sellers and Ops People | 13 March | Due Today
Current Team Phsycological Alignment | Identify the top performers | 13 March | Due Today
No Operation Head | Salary Budget Approval from Karan | 14 March | Upcoming
No Operation Head | Referral Support / Job posting / Vendor | 16 March | Upcoming
No Operation Head | Creating SOP of Hiring | 16 March | Upcoming
Current Team Phsycological Alignment | Physical meet with the PIP Sellers | 18 March | Scheduled
Expand Right Sales Team | Take the inhouse pod hiring requirements from Tarun | 19 March | Scheduled
Expand Right Sales Team | Interviews align & decide panel | 23 March | Scheduled
No Operation Head | Planning time wise his/her first 7 days | 1 May | Scheduled
No Operation Head | DOJ of Candidate | 1 May | Scheduled
No Operation Head | Closing profile and sharing offer letter | 1 April | TBD
Expand Right Sales Team | Role Offers | 6 April | TBD
Expand Right Sales Team | Complete the hiring project | 13 April | TBD
Archit
Issue | Task | Deadline | Status
Geo Politics |  | 18 March | Scheduled
Refund Process | SOP/ Process of Issuing Refunds | 18 March | Scheduled
Refund Process | Clearing pending payments of partners and vendors | 31 March | Scheduled
Refund Process | Clearing customer refunds | 31 March | Scheduled
Bhavna
Issue | Task | Deadline | Status
Geo Politics | Creating Operation Process for FIT | 13 March | Due Today
Geo Politics | USP, Etc) | 13 March | Due Today
Geo Politics | Process Handover to Ops Person By Product (OPS KRA) | 13 March | Due Today
Unified Data System, Reporting & Analysis | Product Head Dashboard Requirement to Nandkishore | 14 March | Upcoming
Geo Politics | Supply | 20 March | Scheduled
Geo Politics | From suppliers as a credit note to cx | 20 March | Scheduled
Bhavna/Tarun
Issue | Task | Deadline | Status
Geo Politics | Cancellation / Date Change / Credit Note Issuance / Etc. | 13 March | Due Today
Deeksha
Issue | Task | Deadline | Status
Geo Politics | Revised Lead change live in the campaigns | 12 March | Overdue
Unified Data System, Reporting & Analysis | Marketing Head Dashboard Requirement to Nandkishore | 14 March | Upcoming
Conv % | Phase 1 (CRM Automations live) | 18 March | Scheduled
Conv % | Feedback + Awareness Ads on Live Lead (Trust Based) | Done | Done
Deeksha/Tarun
Issue | Task | Deadline | Status
Geo Politics | Budget distribution current and domestic | 12 March | Overdue
Loyana
Issue | Task | Deadline | Status
Conv % | Survey of Seller | 13 March | Due Today
Current Team Phsycological Alignment | Take Approval from Karan for people to put on PIP | 16 March | Upcoming
Current Team Phsycological Alignment | Take reward approval from Karan | 16 March | Upcoming
Current Team Phsycological Alignment | Identify issues | 17 March | Scheduled
Current Team Phsycological Alignment | Get rewards delivered | 20 March | Scheduled
Nandkishore
Issue | Task | Deadline | Status
Conv % | Pre Sales TELECRM SETUP DEMO (L1) | 11 March | Overdue
Conv % | Lead Allocation Fix in TELECRM (L1) | 11 March | Overdue
Unified Data System, Reporting & Analysis | L10 Scorecard | 12 March | Overdue
Conv % | Sales SLA tracker Live | 12 March | Overdue
Unified Data System, Reporting & Analysis | EOS | 16 March | Upcoming
Unified Data System, Reporting & Analysis | CEO Dashboard | 16 March | Upcoming
Unified Data System, Reporting & Analysis | Sales Head Dashboard | 16 March | Upcoming
Unified Data System, Reporting & Analysis | Marketing Head Dashboard | 16 March | Upcoming
Unified Data System, Reporting & Analysis | Product Head Dashboard | 16 March | Upcoming
Unified Data System, Reporting & Analysis | Realtime Data Integration | 25 March | Scheduled
Sachin
Issue | Task | Deadline | Status
End to end tech chain | GIT Booking Portal | 13 March | Due Today
End to end tech chain | Cashflow Visibility | 18 March | Scheduled
End to end tech chain | D2C website | 30 March | Scheduled
End to end tech chain | FIT Booking Engine | 15 Apr | Scheduled
Tarun
Issue | Task | Deadline | Status
Geo Politics | Ladakh / Sikkim | 11 March | Overdue
Geo Politics | Shortlisting of Destinations : Domestic / International | 11 March | Overdue
Geo Politics | FIT Operation Executive Alignment | 13 March | Due Today
Unified Data System, Reporting & Analysis | Sales Head Dashboard Requirement to Nandkishore | 14 March | Upcoming
No Operation Head | Required JD for Operation Head | 14 March | Upcoming
No Operation Head | Approving SOP of hiring | 17 March | Scheduled
Current Team Phsycological Alignment | (Clear Old Dues) | 17 March | Scheduled
Expand Right Sales Team | Shortlisting of 10 agencies | 17 March | Scheduled
Conv % | Selection of FIT & GIT Sellers (Pilot Pod) | 18 March | Scheduled
Conv % | Old Lead Allocation | 23 March | Scheduled
Expand Right Sales Team | Meeting 10 agencies | 31 March | Scheduled
Expand Right Sales Team | Quote Comparisons | 31 March | Scheduled
Expand Right Sales Team | Team Live | 15 June | Scheduled
Expand Right Sales Team | Allocating the work | 1 April | TBD

## Weekly Timeline
Issue / Workstream | Task | Owner | W11 09 Mar-15 Mar | W12 16 Mar-22 Mar | W13 23 Mar-29 Mar | W14 30 Mar-05 Apr | W15 06 Apr-12 Apr | W16 13 Apr-19 Apr | W17 20 Apr-26 Apr | W18 27 Apr-03 May | W19 04 May-10 May | W20 11 May-17 May | W21 18 May-24 May | W22 25 May-31 May | W23 01 Jun-07 Jun | W24 08 Jun-14 Jun | W25 15 Jun-21 Jun | W26 22 Jun-28 Jun
Conv % | Pre Sales TELECRM SETUP DEMO (L1) | Nandkishore | ●
Conv % | Lead Allocation Fix in TELECRM (L1) | Nandkishore | ●
Conv % | Sales SLA tracker Live | Nandkishore | ●
Conv % | Survey of Seller | Loyana | ●
Conv % | Selection of FIT & GIT Sellers (Pilot Pod) | Tarun |  | ●
Conv % | Phase 1 (CRM Automations live) | Deeksha |  | ●
Conv % | Old Lead Allocation | Tarun |  |  | ●
Conv % | Feedback + Awareness Ads on Live Lead (Trust Based) | Deeksha
Current Team Phsycological Alignment | Including sellers and Ops People | Anushka | ●
Current Team Phsycological Alignment | Identify the top performers | Anushka | ●
Current Team Phsycological Alignment | Take Approval from Karan for people to put on PIP | Loyana |  | ●
Current Team Phsycological Alignment | Take reward approval from Karan | Loyana |  | ●
Current Team Phsycological Alignment | (Clear Old Dues) | Tarun |  | ●
Current Team Phsycological Alignment | Identify issues | Loyana |  | ●
Current Team Phsycological Alignment | Physical meet with the PIP Sellers | Anushka |  | ●
Current Team Phsycological Alignment | Get rewards delivered | Loyana |  | ●
End to end tech chain | GIT Booking Portal | Sachin | ●
End to end tech chain | Cashflow Visibility | Sachin |  | ●
End to end tech chain | D2C website | Sachin |  |  |  | ●
End to end tech chain | FIT Booking Engine | Sachin | [5 empty] | ●
Expand Right Sales Team | Shortlisting of 10 agencies | Tarun |  | ●
Expand Right Sales Team | Take the inhouse pod hiring requirements from Tarun | Anushka |  | ●
Expand Right Sales Team | Interviews align & decide panel | Anushka |  |  | ●
Expand Right Sales Team | Meeting 10 agencies | Tarun |  |  |  | ●
Expand Right Sales Team | Quote Comparisons | Tarun |  |  |  | ●
Expand Right Sales Team | Team Live | Tarun | [14 empty] | ●
Expand Right Sales Team | Allocating the work | Tarun
Expand Right Sales Team | Role Offers | Anushka
Expand Right Sales Team | Complete the hiring project | Anushka
Geo Politics | Ladakh / Sikkim | Tarun | ●
Geo Politics | Shortlisting of Destinations : Domestic / International | Tarun | ●
Geo Politics | Budget distribution current and domestic | Deeksha/Tarun | ●
Geo Politics | Revised Lead change live in the campaigns | Deeksha | ●
Geo Politics | Creating Operation Process for FIT | Bhavna | ●
Geo Politics | FIT Operation Executive Alignment | Tarun | ●
Geo Politics | USP, Etc) | Bhavna | ●
Geo Politics | Cancellation / Date Change / Credit Note Issuance / Etc. | Bhavna/Tarun | ●
Geo Politics | Process Handover to Ops Person By Product (OPS KRA) | Bhavna | ●
Geo Politics | B2B Air Deals (to Check) | - | ●
Geo Politics |  | Archit |  | ●
Geo Politics | Supply | Bhavna |  | ●
Geo Politics | From suppliers as a credit note to cx | Bhavna |  | ●
No Operation Head | Required JD for Operation Head | Tarun | ●
No Operation Head | Salary Budget Approval from Karan | Anushka | ●
No Operation Head | Referral Support / Job posting / Vendor | Anushka |  | ●
No Operation Head | Creating SOP of Hiring | Anushka |  | ●
No Operation Head | Approving SOP of hiring | Tarun |  | ●
No Operation Head | Planning time wise his/her first 7 days | Anushka | [7 empty] | ●
No Operation Head | DOJ of Candidate | Anushka | [7 empty] | ●
No Operation Head | Closing profile and sharing offer letter | Anushka
Refund Process | SOP/ Process of Issuing Refunds | Archit |  | ●
Refund Process | Clearing pending payments of partners and vendors | Archit |  |  |  | ●
Refund Process | Clearing customer refunds | Archit |  |  |  | ●
Unified Data System, Reporting & Analysis | L10 Scorecard | Nandkishore | ●
Unified Data System, Reporting & Analysis | Sales Head Dashboard Requirement to Nandkishore | Tarun | ●
Unified Data System, Reporting & Analysis | Marketing Head Dashboard Requirement to Nandkishore | Deeksha | ●
Unified Data System, Reporting & Analysis | Product Head Dashboard Requirement to Nandkishore | Bhavna | ●
Unified Data System, Reporting & Analysis | EOS | Nandkishore |  | ●
Unified Data System, Reporting & Analysis | CEO Dashboard | Nandkishore |  | ●
Unified Data System, Reporting & Analysis | Sales Head Dashboard | Nandkishore |  | ●
Unified Data System, Reporting & Analysis | Marketing Head Dashboard | Nandkishore |  | ●
Unified Data System, Reporting & Analysis | Product Head Dashboard | Nandkishore |  | ●
Unified Data System, Reporting & Analysis | Realtime Data Integration | Nandkishore |  |  | ●

## Issue Breakdown
Issue / Workstream | Total Tasks | Overdue | Done | Completion %
Conv % | 8 | 3 | 1 | 12.5%
Current Team Phsycological Alignment | 8 | 0 | 0 | 0%
End to end tech chain | 4 | 0 | 0 | 0%
Expand Right Sales Team | 9 | 0 | 0 | 0%
Geo Politics | 13 | 4 | 0 | 0%
No Operation Head | 8 | 0 | 0 | 0%
Refund Process | 3 | 0 | 0 | 0%
Unified Data System, Reporting & Analysis | 10 | 1 | 0 | 0%
WORKSTREAM TASK DETAILS
Conv % (8 tasks, 3 overdue)
Task | Owner | Deadline | Status
Pre Sales TELECRM SETUP DEMO (L1) | Nandkishore | 11 March | Overdue
Lead Allocation Fix in TELECRM (L1) | Nandkishore | 11 March | Overdue
Sales SLA tracker Live | Nandkishore | 12 March | Overdue
Survey of Seller | Loyana | 13 March | Due Today
Selection of FIT & GIT Sellers (Pilot Pod) | Tarun | 18 March | Scheduled
Phase 1 (CRM Automations live) | Deeksha | 18 March | Scheduled
Old Lead Allocation | Tarun | 23 March | Scheduled
Feedback + Awareness Ads on Live Lead (Trust Based) | Deeksha | Done | Done
Current Team Phsycological Alignment (8 tasks, 0 overdue)
Task | Owner | Deadline | Status
Including sellers and Ops People | Anushka | 13 March | Due Today
Identify the top performers | Anushka | 13 March | Due Today
Take Approval from Karan for people to put on PIP | Loyana | 16 March | Upcoming
Take reward approval from Karan | Loyana | 16 March | Upcoming
(Clear Old Dues) | Tarun | 17 March | Scheduled
Identify issues | Loyana | 17 March | Scheduled
Physical meet with the PIP Sellers | Anushka | 18 March | Scheduled
Get rewards delivered | Loyana | 20 March | Scheduled
End to end tech chain (4 tasks, 0 overdue)
Task | Owner | Deadline | Status
GIT Booking Portal | Sachin | 13 March | Due Today
Cashflow Visibility | Sachin | 18 March | Scheduled
D2C website | Sachin | 30 March | Scheduled
FIT Booking Engine | Sachin | 15 Apr | Scheduled
Expand Right Sales Team (9 tasks, 0 overdue)
Task | Owner | Deadline | Status
Shortlisting of 10 agencies | Tarun | 17 March | Scheduled
Take the inhouse pod hiring requirements from Tarun | Anushka | 19 March | Scheduled
Interviews align & decide panel | Anushka | 23 March | Scheduled
Meeting 10 agencies | Tarun | 31 March | Scheduled
Quote Comparisons | Tarun | 31 March | Scheduled
Team Live | Tarun | 15 June | Scheduled
Allocating the work | Tarun | 1 April | TBD
Role Offers | Anushka | 6 April | TBD
Complete the hiring project | Anushka | 13 April | TBD
Geo Politics (13 tasks, 4 overdue)
Task | Owner | Deadline | Status
Ladakh / Sikkim | Tarun | 11 March | Overdue
Shortlisting of Destinations : Domestic / International | Tarun | 11 March | Overdue
Budget distribution current and domestic | Deeksha/Tarun | 12 March | Overdue
Revised Lead change live in the campaigns | Deeksha | 12 March | Overdue
Creating Operation Process for FIT | Bhavna | 13 March | Due Today
FIT Operation Executive Alignment | Tarun | 13 March | Due Today
USP, Etc) | Bhavna | 13 March | Due Today
Cancellation / Date Change / Credit Note Issuance / Etc. | Bhavna/Tarun | 13 March | Due Today
Process Handover to Ops Person By Product (OPS KRA) | Bhavna | 13 March | Due Today
B2B Air Deals (to Check) | - | 13 March | Due Today
| Archit | 18 March | Scheduled
Supply | Bhavna | 20 March | Scheduled
From suppliers as a credit note to cx | Bhavna | 20 March | Scheduled
No Operation Head (8 tasks, 0 overdue)
Task | Owner | Deadline | Status
Required JD for Operation Head | Tarun | 14 March | Upcoming
Salary Budget Approval from Karan | Anushka | 14 March | Upcoming
Referral Support / Job posting / Vendor | Anushka | 16 March | Upcoming
Creating SOP of Hiring | Anushka | 16 March | Upcoming
Approving SOP of hiring | Tarun | 17 March | Scheduled
Planning time wise his/her first 7 days | Anushka | 1 May | Scheduled
DOJ of Candidate | Anushka | 1 May | Scheduled
Closing profile and sharing offer letter | Anushka | 1 April | TBD
Refund Process (3 tasks, 0 overdue)
Task | Owner | Deadline | Status
SOP/ Process of Issuing Refunds | Archit | 18 March | Scheduled
Clearing pending payments of partners and vendors | Archit | 31 March | Scheduled
Clearing customer refunds | Archit | 31 March | Scheduled
Unified Data System, Reporting & Analysis (10 tasks, 1 overdue)
Task | Owner | Deadline | Status
L10 Scorecard | Nandkishore | 12 March | Overdue
Sales Head Dashboard Requirement to Nandkishore | Tarun | 14 March | Upcoming
Marketing Head Dashboard Requirement to Nandkishore | Deeksha | 14 March | Upcoming
Product Head Dashboard Requirement to Nandkishore | Bhavna | 14 March | Upcoming
EOS | Nandkishore | 16 March | Upcoming
CEO Dashboard | Nandkishore | 16 March | Upcoming
Sales Head Dashboard | Nandkishore | 16 March | Upcoming
Marketing Head Dashboard | Nandkishore | 16 March | Upcoming
Product Head Dashboard | Nandkishore | 16 March | Upcoming
Realtime Data Integration | Nandkishore | 25 March | Scheduled

## Kanban Board
OVERDUE | DUE TODAY | UPCOMING | SCHEDULED | DONE
8 tasks | 10 tasks | 14 tasks | 26 tasks | 1 task
Geo Politics | Geo Politics | Unified Data System, Reporting & Analysis | No Operation Head | Conv %
Ladakh / Sikkim | Creating Operation Process for FIT | Sales Head Dashboard Requirement to Nandkishore | Approving SOP of hiring | Feedback + Awareness Ads on Live Lead (Trust Based)
👤 Tarun ¦ 📅 11 March | 👤 Bhavna ¦ 📅 13 March | 👤 Tarun ¦ 📅 14 March | 👤 Tarun ¦ 📅 17 March | 👤 Deeksha ¦ 📅 Done
Geo Politics | Geo Politics | Unified Data System, Reporting & Analysis | Current Team Phsycological Alignment
Shortlisting of Destinations : Domestic / International | FIT Operation Executive Alignment | Marketing Head Dashboard Requirement to Nandkishore | (Clear Old Dues)
👤 Tarun ¦ 📅 11 March | 👤 Tarun ¦ 📅 13 March | 👤 Deeksha ¦ 📅 14 March | 👤 Tarun ¦ 📅 17 March
Conv % | Geo Politics | Unified Data System, Reporting & Analysis | Expand Right Sales Team
Pre Sales TELECRM SETUP DEMO (L1) | USP, Etc) | Product Head Dashboard Requirement to Nandkishore | Shortlisting of 10 agencies
👤 Nandkishore ¦ 📅 11 March | 👤 Bhavna ¦ 📅 13 March | 👤 Bhavna ¦ 📅 14 March | 👤 Tarun ¦ 📅 17 March
Conv % | Geo Politics | No Operation Head | Current Team Phsycological Alignment
Lead Allocation Fix in TELECRM (L1) | Cancellation / Date Change / Credit Note Issuance / Etc. | Required JD for Operation Head | Identify issues
👤 Nandkishore ¦ 📅 11 March | 👤 Bhavna/Tarun ¦ 📅 13 March | 👤 Tarun ¦ 📅 14 March | 👤 Loyana ¦ 📅 17 March
Unified Data System, Reporting & Analysis | Geo Politics | No Operation Head | Geo Politics
L10 Scorecard | Process Handover to Ops Person By Product (OPS KRA) | Salary Budget Approval from Karan | (No description)
👤 Nandkishore ¦ 📅 12 March | 👤 Bhavna ¦ 📅 13 March | 👤 Anushka ¦ 📅 14 March | 👤 Archit ¦ 📅 18 March
Geo Politics | Geo Politics | Unified Data System, Reporting & Analysis | Conv %
Budget distribution current and domestic | B2B Air Deals (to Check) | EOS | Selection of FIT & GIT Sellers (Pilot Pod)
👤 Deeksha/Tarun ¦ 📅 12 March | 👤 - ¦ 📅 13 March | 👤 Nandkishore ¦ 📅 16 March | 👤 Tarun ¦ 📅 18 March
Geo Politics | Conv % | Unified Data System, Reporting & Analysis | Refund Process
Revised Lead change live in the campaigns | Survey of Seller | CEO Dashboard | SOP/ Process of Issuing Refunds
👤 Deeksha ¦ 📅 12 March | 👤 Loyana ¦ 📅 13 March | 👤 Nandkishore ¦ 📅 16 March | 👤 Archit ¦ 📅 18 March
Conv % | End to end tech chain | Unified Data System, Reporting & Analysis | Current Team Phsycological Alignment
Sales SLA tracker Live | GIT Booking Portal | Sales Head Dashboard | Physical meet with the PIP Sellers
👤 Nandkishore ¦ 📅 12 March | 👤 Sachin ¦ 📅 13 March | 👤 Nandkishore ¦ 📅 16 March | 👤 Anushka ¦ 📅 18 March
| Current Team Phsycological Alignment | Unified Data System, Reporting & Analysis | End to end tech chain
| Including sellers and Ops People | Marketing Head Dashboard | Cashflow Visibility
| 👤 Anushka ¦ 📅 13 March | 👤 Nandkishore ¦ 📅 16 March | 👤 Sachin ¦ 📅 18 March
| Current Team Phsycological Alignment | Unified Data System, Reporting & Analysis | Conv %
| Identify the top performers | Product Head Dashboard | Phase 1 (CRM Automations live)
| 👤 Anushka ¦ 📅 13 March | 👤 Nandkishore ¦ 📅 16 March | 👤 Deeksha ¦ 📅 18 March
|  | No Operation Head | Expand Right Sales Team
|  | Referral Support / Job posting / Vendor | Take the inhouse pod hiring requirements from Tarun
|  | 👤 Anushka ¦ 📅 16 March | 👤 Anushka ¦ 📅 19 March
|  | No Operation Head | Geo Politics
|  | Creating SOP of Hiring | Supply
|  | 👤 Anushka ¦ 📅 16 March | 👤 Bhavna ¦ 📅 20 March
|  | Current Team Phsycological Alignment | Geo Politics
|  | Take Approval from Karan for people to put on PIP | From suppliers as a credit note to cx
|  | 👤 Loyana ¦ 📅 16 March | 👤 Bhavna ¦ 📅 20 March
|  | Current Team Phsycological Alignment | Current Team Phsycological Alignment
|  | Take reward approval from Karan | Get rewards delivered
|  | 👤 Loyana ¦ 📅 16 March | 👤 Loyana ¦ 📅 20 March
Conv %
Old Lead Allocation
👤 Tarun ¦ 📅 23 March
Expand Right Sales Team
Interviews align & decide panel
👤 Anushka ¦ 📅 23 March
Unified Data System, Reporting & Analysis
Realtime Data Integration
👤 Nandkishore ¦ 📅 25 March
End to end tech chain
D2C website
👤 Sachin ¦ 📅 30 March
Expand Right Sales Team
Meeting 10 agencies
👤 Tarun ¦ 📅 31 March
Expand Right Sales Team
Quote Comparisons
👤 Tarun ¦ 📅 31 March
Refund Process
Clearing pending payments of partners and vendors
👤 Archit ¦ 📅 31 March
Refund Process
Clearing customer refunds
👤 Archit ¦ 📅 31 March
End to end tech chain
FIT Booking Engine
👤 Sachin ¦ 📅 15 Apr
No Operation Head
Planning time wise his/her first 7 days
👤 Anushka ¦ 📅 1 May
No Operation Head
DOJ of Candidate
👤 Anushka ¦ 📅 1 May
Expand Right Sales Team
Team Live
👤 Tarun ¦ 📅 15 June

## PERT & Dependencies
PERT-STYLE CRITICAL PATH ANALYSIS
Tasks grouped by workstream, ordered by deadline. Earliest-start/latest-finish identifies bottleneck paths.
Workstream | Task | Owner | Deadline | Start (Earliest) | Duration (days) | Slack | Critical?
Conv % | Pre Sales TELECRM SETUP DEMO (L1) | Nandkishore | 2026-03-11 | 2026-03-10 | 1 | 0 | YES
Conv % | Lead Allocation Fix in TELECRM (L1) | Nandkishore | 2026-03-11 | 2026-03-10 | 1 | 0 | YES
Conv % | Sales SLA tracker Live | Nandkishore | 2026-03-12 | 2026-03-11 | 1 | 0 | YES
Conv % | Survey of Seller | Loyana | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Conv % | Selection of FIT & GIT Sellers (Pilot Pod) | Tarun | 2026-03-18 | 2026-03-13 | 5 | 5 | No
Conv % | Phase 1 (CRM Automations live) | Deeksha | 2026-03-18 | 2026-03-17 | 1 | 5 | No
Conv % | Old Lead Allocation | Tarun | 2026-03-23 | 2026-03-18 | 5 | 10 | No
Current Team Phsycological Alignment | Including sellers and Ops People | Anushka | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Current Team Phsycological Alignment | Identify the top performers | Anushka | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Current Team Phsycological Alignment | Take Approval from Karan for people to put on PIP | Loyana | 2026-03-16 | 2026-03-13 | 3 | 3 | No
Current Team Phsycological Alignment | Take reward approval from Karan | Loyana | 2026-03-16 | 2026-03-15 | 1 | 3 | No
Current Team Phsycological Alignment | (Clear Old Dues) | Tarun | 2026-03-17 | 2026-03-16 | 1 | 4 | No
Current Team Phsycological Alignment | Identify issues | Loyana | 2026-03-17 | 2026-03-16 | 1 | 4 | No
Current Team Phsycological Alignment | Physical meet with the PIP Sellers | Anushka | 2026-03-18 | 2026-03-17 | 1 | 5 | No
Current Team Phsycological Alignment | Get rewards delivered | Loyana | 2026-03-20 | 2026-03-18 | 2 | 7 | No
End to end tech chain | GIT Booking Portal | Sachin | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
End to end tech chain | Cashflow Visibility | Sachin | 2026-03-18 | 2026-03-13 | 5 | 5 | No
End to end tech chain | D2C website | Sachin | 2026-03-30 | 2026-03-18 | 12 | 17 | No
End to end tech chain | FIT Booking Engine | Sachin | 2026-04-15 | 2026-03-30 | 16 | 33 | No
Expand Right Sales Team | Shortlisting of 10 agencies | Tarun | 2026-03-17 | 2026-03-16 | 1 | 4 | No
Expand Right Sales Team | Take the inhouse pod hiring requirements from Tarun | Anushka | 2026-03-19 | 2026-03-17 | 2 | 6 | No
Expand Right Sales Team | Interviews align & decide panel | Anushka | 2026-03-23 | 2026-03-19 | 4 | 10 | No
Expand Right Sales Team | Meeting 10 agencies | Tarun | 2026-03-31 | 2026-03-23 | 8 | 18 | No
Expand Right Sales Team | Quote Comparisons | Tarun | 2026-03-31 | 2026-03-30 | 1 | 18 | No
Expand Right Sales Team | Team Live | Tarun | 2026-06-15 | 2026-03-31 | 76 | 94 | No
Geo Politics | Ladakh / Sikkim | Tarun | 2026-03-11 | 2026-03-10 | 1 | 0 | YES
Geo Politics | Shortlisting of Destinations : Domestic / International | Tarun | 2026-03-11 | 2026-03-10 | 1 | 0 | YES
Geo Politics | Budget distribution current and domestic | Deeksha/Tarun | 2026-03-12 | 2026-03-11 | 1 | 0 | YES
Geo Politics | Revised Lead change live in the campaigns | Deeksha | 2026-03-12 | 2026-03-11 | 1 | 0 | YES
Geo Politics | Creating Operation Process for FIT | Bhavna | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics | FIT Operation Executive Alignment | Tarun | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics | USP, Etc) | Bhavna | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics | Cancellation / Date Change / Credit Note Issuance / Etc. | Bhavna/Tarun | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics | Process Handover to Ops Person By Product (OPS KRA) | Bhavna | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics | B2B Air Deals (to Check) | - | 2026-03-13 | 2026-03-12 | 1 | 0 | YES
Geo Politics |  | Archit | 2026-03-18 | 2026-03-13 | 5 | 5 | No
Geo Politics | Supply | Bhavna | 2026-03-20 | 2026-03-18 | 2 | 7 | No
Geo Politics | From suppliers as a credit note to cx | Bhavna | 2026-03-20 | 2026-03-19 | 1 | 7 | No
No Operation Head | Required JD for Operation Head | Tarun | 2026-03-14 | 2026-03-13 | 1 | 1 | No
No Operation Head | Salary Budget Approval from Karan | Anushka | 2026-03-14 | 2026-03-13 | 1 | 1 | No
No Operation Head | Referral Support / Job posting / Vendor | Anushka | 2026-03-16 | 2026-03-14 | 2 | 3 | No
No Operation Head | Creating SOP of Hiring | Anushka | 2026-03-16 | 2026-03-15 | 1 | 3 | No
No Operation Head | Approving SOP of hiring | Tarun | 2026-03-17 | 2026-03-16 | 1 | 4 | No
No Operation Head | Planning time wise his/her first 7 days | Anushka | 2026-05-01 | 2026-03-17 | 45 | 49 | No
No Operation Head | DOJ of Candidate | Anushka | 2026-05-01 | 2026-04-30 | 1 | 49 | No
Refund Process | SOP/ Process of Issuing Refunds | Archit | 2026-03-18 | 2026-03-17 | 1 | 5 | No
Refund Process | Clearing pending payments of partners and vendors | Archit | 2026-03-31 | 2026-03-18 | 13 | 18 | No
Refund Process | Clearing customer refunds | Archit | 2026-03-31 | 2026-03-30 | 1 | 18 | No
Unified Data System, Reporting & Analysis | L10 Scorecard | Nandkishore | 2026-03-12 | 2026-03-11 | 1 | 0 | YES
Unified Data System, Reporting & Analysis | Sales Head Dashboard Requirement to Nandkishore | Tarun | 2026-03-14 | 2026-03-12 | 2 | 1 | No
Unified Data System, Reporting & Analysis | Marketing Head Dashboard Requirement to Nandkishore | Deeksha | 2026-03-14 | 2026-03-13 | 1 | 1 | No
Unified Data System, Reporting & Analysis | Product Head Dashboard Requirement to Nandkishore | Bhavna | 2026-03-14 | 2026-03-13 | 1 | 1 | No
Unified Data System, Reporting & Analysis | EOS | Nandkishore | 2026-03-16 | 2026-03-14 | 2 | 3 | No
Unified Data System, Reporting & Analysis | CEO Dashboard | Nandkishore | 2026-03-16 | 2026-03-15 | 1 | 3 | No
Unified Data System, Reporting & Analysis | Sales Head Dashboard | Nandkishore | 2026-03-16 | 2026-03-15 | 1 | 3 | No
Unified Data System, Reporting & Analysis | Marketing Head Dashboard | Nandkishore | 2026-03-16 | 2026-03-15 | 1 | 3 | No
Unified Data System, Reporting & Analysis | Product Head Dashboard | Nandkishore | 2026-03-16 | 2026-03-15 | 1 | 3 | No
Unified Data System, Reporting & Analysis | Realtime Data Integration | Nandkishore | 2026-03-25 | 2026-03-16 | 9 | 12 | No